## Sheet1
Sprint Burndown Chart - Etapa 9
Backlog ID | User Stories | Estimativa Inicial | 2021-11-26 | 2021-11-27 | 2021-11-28 | 2021-11-29 | 2021-11-30 | 2021-12-01 | 2021-12-02 | 2021-12-03 | 2021-12-04 | 2021-12-05 | 2021-12-06 | 2021-12-07 | 2021-12-08 | 2021-12-09 | 2021-12-10 | 2021-12-11 | 2021-12-12 | 2021-12-13 | 2021-12-14 | 2021-12-15 | 2021-12-16
|  |  | Dia 1 | Dia 2 | Dia 3 | Dia 4 | Dia 5 | Dia 6 | Dia 7 | Dia 8 | Dia 9 | Dia 10 | Dia 11 | Dia 12 | Dia 13 | Dia 14 | Dia 15 | Dia 16 | Dia 17 | Dia 18 | Dia 19 | Dia 20 | Dia 21
1 | Pagina Dinamica Rui Costa | 30 | 2 | 2 | 2 |  |  | 3 | 2 |  |  | 2 | 2 | 2 | 2 | 3 | 3 | 2 |  | 2 | 3
2 | Pagina Dinamica Pedro Guerra | 30 | 2021-11-26: 3; 2021-11-27: 3; 2021-11-28: 1; 2021-11-30: 1; 2021-12-01: 1; 2021-12-04: 3; 2021-12-06: 2; 2021-12-07: 2; 2021-12-09: 1; 2021-12-11: 2; 2021-12-12: 2; 2021-12-14: 3
3 | Pagina Dinamica João Peres | 30 | 2021-11-26: 3; 2021-11-27: 3; 2021-11-28: 3; 2021-11-29: 3; 2021-11-30: 3; 2021-12-01: 3; 2021-12-02: 3; 2021-12-03: 3; 2021-12-04: 3; 2021-12-05: 3
4 | Pagina Dinamica Francisco Borges | 30
5 | Pagina Dinamica Ricardo Santos | 30
6 | Script Base de Dados | 20 | 2021-11-26: 3; 2021-11-29: 3; 2021-12-02: 5; 2021-12-03: 5; 2021-12-05: 3; 2021-12-07: 1
7 | Mapa de Navegaçao | 4 | 2021-12-12: 2; 2021-12-13: 2
8 | Descrição do backoffice | 5 | 2021-12-14: 3; 2021-12-15: 2
9 | Metodologia de Projeto | 2
10 | Planeamento de Tarefas | 2 | 2021-11-28: 2
11 | Relatorio Etapa 9 | 2
Remaining Effort |  | 185 | 11 | 8 | 8 | 6 | 4 | 7 | 10 | 8 | 6 | 8 | 4 | 5 | 2 | 4 | 3 | 4 | 4 | 4 | 9 | 2 | 0
Ideal Trend |  | 185 | 11 | 8 | 8 | 6 | 4 | 7 | 10 | 8 | 6 | 8 | 4 | 5 | 2 | 4 | 3 | 4 | 4 | 4 | 9 | 2 | 0
Note on A1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: https://www.youtube.com/watch?v=J17dOgmjS2c